## Agile Task Board
Happnix WebAPP | [8 empty] | Happnix MobileAPP
Task ID | Task Name | Priority | Assignee | Status | Type | Notes | Start Date | Due Date | Task ID | Task Name | Priority | Assignee | Status | Type | Notes | Start Date | Due Date
T001 | Flexible ticket pricee | Low | Ronak | To Do | Feature |  |  |  | T001 |  |  | Ronak | To do
T002 | Price increment timer | Low | Ronak | To Do | Feature |  |  |  | T002 |  |  | Ronak | To do
T003 | Event Details in event card | Medium | Ronak | To Do | Feature |  |  |  | T003 |  |  | Ronak | To do
T004 | Ticket Details to user | Medium | Ronak | To Do | Feature |  |  |  | T004 |  |  | Ronak | To do
T005 | Profile section detailing | Medium | Ronak | To Do | Feature |  |  |  | T005 |  |  | Ronak | To do
T007 | subevents in event | Low | Ronak | In Progress | Feature |  |  |  | T006 |  |  | Ronak | To do
T008 | App theme redesign | Low | Ronak | To Do | Rework |  |  |  | T007 |  |  | Ronak | To do
T009 | Theme of Event categories | Low | Ronak | To Do | Feature |  |  |  | T008 |  |  | Ronak | To do
T012 | Group Ticket booking | Medium | Ronak | To Do | Feature |  |  |  | T009 |  |  | Ronak | To do
T013 | Archive Event option | Low | Ronak | To Do | Feature |  |  |  | T010 |  |  | Ronak | To do
T014 | diffenciate Upcoming, running, Ended Event | Medium | Ronak | To Do | Feature |  |  |  | T011 |  |  | Ronak | To do
T015 | Feed to see Post and Events | High | Ronak | In Progress | Feature |  |  |  | T012 |  |  | Ronak | To do
T016 | Discover section to design and show Events and post | High | Ronak | To Do | Feature |  |  |  | T013 |  |  | Ronak | To do
T018 | Live updates from server without reload | Medium | Ronak | In Progress | Feature |  |  |  | T014 |  |  | Ronak | To do
T019 | switch to business account, and get varfied sign to stand out as varfied page | Low | Ronak | To Do | Feature |  |  |  | T015 |  |  | Ronak | To do
T020 | PlatForm fee structure to the user who are booking the tickets of an event | Low | Ronak | To Do | Feature |  |  |  | T016 |  |  | Ronak | To do
T021 | how to handle event with the same name | Low | Ronak | To Do | Feature |  |  |  | T017 |  |  | Ronak | To do
T022 | turn on Like and comment section and show it to the users | Medium | Ronak | To Do | Feature
T023 | Message feature for the user | High | Ronak | To Do | Feature
T024 | Add a feature to make partner event | Medium | Ronak | To Do | Feature
T025 | Edit-Delete-unsend-Forward-Reply-info in message option | Medium | Ronak | In Progress | Feature | Reply-info to be add
T028 | Add active stauts in the chat | High | Ronak | To Do | Feature
T029 | Show typing status in chats | High | Ronak | To Do | Feature
T030 | Design chat option corretly for mobile mode | High | Ronak | To Do | Bug
T031 | Create Group in messages | Medium | Ronak | To Do | Feature
T032 | Add request method for those who are not Followed by the user you chat | High | Ronak | To Do | Feature

## Aglie Task completed
HappniX WebApp | [8 empty] | HappniX MobileApp
Task ID | Task Name | Priority | Assignee | Status | Type | Notes | Start Date | Due Date | Task ID | Task Name | Priority | Assignee | Status | Type | Notes | Start Date | Due Date
T006 | search user profile and event in discover page | Low | Ronak | Done | Feature | need to review |  |  | T001 |  |  | Ronak | Done
T010 | HappniX logo creation | Medium | Ronak | Done | Feature | done for now |  |  | T002
T011 | Add Following Follower option | Medium | Ronak | Done | Feature | done for now |  |  | T003
T017 | Private account and respective updatation | Medium | Ronak | Done | Feature | done for now |  |  | T004
T023 | Live now section In for you section | Medium | Ronak | Done | Feature | done for now
T024 | Join now button will show even after user joins in | High | Ronak | Fixed | Bug
T023 | Message feature for the user | High | Ronak | Done | Feature
T026 | Add attachment and voice note feature in chat | Medium | Ronak | Done | Feature
T027 | Real time web socket in chats | Medium | Ronak | Done | Feature

## Added Features list Web
Added Feature list Happnix Web
Featues | Status | Notes
Signin Signup Page with phone number, email and username | Done | Otp service Required
Signup form | Done | Email and Adhar varify and Remove 18+ necessity
Forget password | Done | required to share link via email to forget password
Home page for mobile and desktop mode | Done | Need to redesign the layout
Notification panel | Done | Need to work a little bit more in that
Location services with live location to map selected location and manually input location | Done | Currently using open street map but need to use google maps
Post Feed (For You) | Done | Currently showing post only for the followings
Private Account setting | Done | Need to review
Follwing and followers (Fans) Add, remove, follow back and request in private accoutn | Done | Need to review
Discover user profile using username and full name | Done | Need to review
Adhar varification Alert notification | Done | Need to connect with adhar varification API
Adhar varified can use the service like host and event and buy a ticket | Done | Currently off due to Adhar authentiction Api not integrated
Happnix small and big Logo | Done | using currently, open for redesign
Event and post upload | Done | more details could add in both
Event could be free and Paid with limited seats and flexible seating options | Done | Working fine
Seating options in paid ticket options | Done | Working fine
Post could attach with Event as Pre and Post highlight | Done | Need to review
Time and Date pop up | Done | Need to review
Ticket and event card showing in my events | Done | Need to work on the details of the cards
Ticket will be shown as free or paid and if paid then which section to book in free | Done | Need to work on this
Ticket and event card neon light border shadows | Done | Look fine
Profile with username, fullname, fan and follwing details and Vibe (event and post) details | Done | Need to work
Event and ticket could delete | Done | Need to introduce more option
Logout button | Done | Working fine
View searched user profile with basic details like username, fullname, fan and follwing details and Vibe (event and post) details | Done | Need to work
User can upload 9 photo/videos(90sec) and 1 cover photo(must) in event section | Done | Need to work
User can upload 10 photo/video(90sec) in Post section where atleast 1 photo/video is must | Done | Need to work
Swipe button in event creation section | Done | Working fine
Live now section Added which show live event which are currently in running | Done | Need to review
user can cancel the ticket now | Done | Working fine
user cannot join the event if already joined | Done | Working fine
Messaging Feature with all the necessary requirements | Done | Need to work

## Added Features list Mobile
Added Feature list Happnix Mobile
Featues | Status | Notes

## Addition changes
Task ID | Task Name | Priority | Assignee | Status | Start Date | Due Date | Notes
T001 | Database Design proper
T002 | Varification of Email
T003 | Forget password
T004 | Adhar card varification
T005 | Mobile Otp service
T006 | QR Code
T007 | Event Heat map
T008 | Rules in event category
T009 | Redefine manifest file
T010 | intoduction of premium plans
T011 | Boost Event
T012 | Aws Integration
T013 | Proper App Designing
T014 | Animation Designing